## Slide 1: Problem Statement
Problem Statement
Address the inefficient maintenance of campus green spaces due to limited resources and increasing environmental pressures.
User Needs Discovered Through Empathy Exercises
Students: Aesthetic, healthy campus environment; easy participation in plant care.
Campus Managers: Efficient, sustainable maintenance; system for direct plant status identification.
Sanitation Workers: Clear plant maintenance guidance; reduced workload.

## Slide 2: Project Timeline
Timeline
Phase: Initiation
Time: Week 1
Milestones:
Define scope, objectives, team roles
Phase: Research & Analysis
Time: Week 2-4
Milestones:
Interview stakeholders
analyze processes
identify issues
Phase: System Design
Time: Week 5-6
Milestones:
Develop architecture,
Design UI for different users
Establish data methods
Phase: Development & Testing
Time: Week 7-10
Milestones:
Build system
Implement features
Test with feedback
Phase: Implementation & Deployment
Time: Week 11-12
Milestones:
Deploy system
Train users
Create educational materials
Phase: Closure
Time: Week 13
Milestones:
Evaluate outcomes,
Document lessons,
Present deliverables